## Sheet1
Responsibility Assignment Matrix
Broadband Equity, Access and Deployment Construction Management Services Request for Proposals (RFP) BL2026_07
Responsible (R): The individual or team who performs the work or executes the task.
Accountable (A): The person ultimately answerable for the outcome, approval, or final decision.
Consulted (C): People who provide subject matter expertise, input, or review before decisions or actions occur.
Informed (I): People who need awareness of progress, decisions, or outcomes but are not directly involved in execution or decision-making.
| Broadlinc | OSP | Const. Mgmt | Engineer | Const.
1. Program Coordination and Project Administration
Activities associated with overall project execution, schedule coordination, issue resolution, and stakeholder communication.
Weekly project and contractor coordination meetings | I | A | R | C | C
Coordination between engineering, construction, vendors, utilities, and Broadlinc staff | I | R | A | C | C
Construction readiness coordination (Notice to Proceed) | I | C | A | R | I
Milestone and implementation tracking | C | R | A | R | R
Coordination of construction sequencing and deployment timing | A | C | R | I | I
Support for internal approval workflows and escalation processes | A | R | C | I | I
Change management coordination and documentation | A | C | R | I | I
Construction contract execution support | A | C | R | I | I
Cross-functional coordination between field, procurement, permitting, and compliance teams | A | R | C | I | I
Coordination of project implementation across simultaneous deployment areas | C | R | A | I | I
Risk and Issue tracking | I | R | A | C | C
2. Engineering Review and Field Validation
Activities associated with validating constructability, design accuracy, network performance, and alignment with approved project scopes.
Field validation of aerial and underground routes | I | C | C | A | R
Pole-by-pole aerial review | I | A | C | R | I
Constructability assessments | I | C | C | A | R
Aerial and underground design review | I | C | C | A | R
FTTH topology validation | I | R | C | A | C
Backbone and fiber ring architecture review | A | R | C | I | I
RF propagation and coverage assessment | A | I | C | R | I
Backhaul design and redundancy coordination | A | R | C | I | I
Verification of engineering alignment with approved service areas | A | R | C | I | I
Identification and resolution of field conflicts requiring design modification | I | C | C | A | R
Review of utility plant conditions affecting construction readiness | I | A | I | R | C
Validation of make-ready requirements and attachment feasibility | I | A | I | R | C
3. Permitting, Environmental, and Utility Coordination
Activities associated with obtaining, coordinating, and maintaining permits and approvals necessary for construction.
Right-of-way permit coordination | R | A | C | I | I
Utility crossing and attachment permitting | R | A | C | I | I
Traffic control plan coordination and review | I | C | C | R | A
Environmental permit coordination | R | A | C | I | I
SEPA and environmental review coordination | A | R | C | C | I
Utility owner coordination and make-ready communication | R | A | C | I | I
WSDOT and local jurisdiction coordination | I | C | C | A | R
County planning coordination | A | R | C | I | I
Permit deliverable preparation and submission | A | R | C | C | I
Escalation and resolution of jurisdictional review delays | A | R | C | C | I
Ongoing permit status tracking and compliance monitoring | C | R | A | I | I
4. Materials Procurement and Supply Chain Coordination
Activities associated with procurement planning, vendor coordination, and material availability management.
Vendor outreach and procurement coordination | A | C | R | C | C
Materials sourcing, availability verification, and sequencing | A | C | R | C | C
Lead-time and supply chain monitoring | A | C | R | C | C
BOM development and finalization | I | A | R | R | C
Procurement schedule coordination aligned with construction sequencing | A | C | R | I | C
Material pricing review and volatility monitoring | A | C | R | C | I
Procurement support for change orders and revised quantities | A | C | R | C | C
Coordination of staged delivery and storage logistics | I | A | R | I | C
Construction readiness verification for procured materials | I | A | C | I | R
Vendor quote collection and evaluation | A | R | C | I | I
Material Traceability and inventory coordination | A | C | R | C | C
5. Federal Compliance and Procurement Documentation
Activities associated with maintaining compliance with federal grant requirements and procurement standards.
BABA compliance review and documentation validation | A | R | I | C | I
Vendor certification review | A | C | R | I | I
Federal sourcing verification | A | C | R | I | I
Procurement documentation and compliance review | A | C | R | I | I
Competitive procurement support | A | C | R | I | I
Inventory traceability and documentation management | A | C | R | I | I
Materials acquisition recordkeeping | A | C | R | I | I
Compliance-focused vendor meetings | A | C | R | I | I
Contractor insurance and permit verification | A | C | R | I | I
Grant compliance documentation support | A | C | R | I | I
Validation that procurement activities align with approved grant scope and budget | A | C | R | I | I
6. Construction Oversight and Readiness Coordination
Activities associated with preparing projects for active construction and supporting ongoing field implementation.
Contractor readiness review | C | R | A | I | I
Labor and equipment coordination meetings | I | C | A | I | R
Construction Stage Readiness Validation | C | R | A | C | C
Verification of construction sequencing | I | C | A | I | R
Review of contractor scope alignment | I | C | A | I | R
Coordination between engineering and construction teams | I | C | A | R | R
Support for field issue resolution | I | C | A | C | R
Construction startup coordination | I | C | A | I | R
Review of traffic control and field safety readiness | I | C | A | I | R
Monitoring field adjustments requiring engineering response | I | C | A | R | R
Coordination of revised field routing and construction modifications | I | C | A | R | R
7. GIS, Reporting, and Construction Tracking Systems
Activities associated with project visibility, reporting, and infrastructure tracking.
GIS coordination and design integration | I | A | I | R | C
Construction progress dashboard development | I | C | A | R | C
Tracking of planned vs constructed infrastructure | I | C | A | R | C
Fiber route and splice tracking | I | C | A | R | C
Pole attachment status tracking | I | C | A | R | C
Cabinet, vault, conduit, and handhole mapping | I | C | R | A | C
Progress reporting support | I | C | A | R | C
Construction status visualization | I | C | R | A | C
Data integration between engineering and construction systems | I | C | R | A | C
Documentation management supporting grant reporting and reimbursement | A | C | R | I | I
8. Network Equipment and Technology Evaluation
Activities associated with evaluating network equipment compatibility, performance, and operational alignment.
ONT/NID equipment Order | A | C | R | C | I
Cabinet and environmental enclosure review | A | C | R | C | I
Capacity and scalability review | A | C | I | R | I
Long-term operational suitability analysis | A | C | I | R | I
Review of network performance alignment with grant speed obligations | A | R | C | I | I
Deployment Sequencing coordination | A | C | R | C | C