# Attachment C - SS4A Project One-Page Summary

| Purpose This one-page plan summarizes how Green River will deliver its Safe Streets and Roads for All (SS4A) Planning and Demonstration Grant in a coordinated, efficient, and FHWA-compliant manner. The project will use a consultant-led model suited to a small rural community. City staff retain policy direction, grant administration, fiscal oversight, and final approval of all activities and deliverables. | Delivery model - Consultant manages day-to-day technical work and project coordination. - City manages policy direction, approvals, fiscal oversight, and reimbursement documentation. - FHWA Utah Division provides kickoff, compliance guidance, and review at key milestones. |
| --- | --- |

Delivery principle: The City retains policy direction, grant administration, fiscal oversight, and final approval of all SS4A project activities and deliverables throughout the life of the grant

# Delivery Framework

| 1 GRANT EXECUTION Agreement, NTP, contacts, accounting, match tracking, coordination protocols. | 2 FHWA KICKOFF Confirm schedule, roles, scope, , milestones, and reporting.. | 3 PROCURE CONSULTANT Qualifications-based procurement; finalize scope, fee, contract, and work plan. | 4 TECHNICAL WORK Crash analysis, risks, countermeasures, costs, phasing, preliminary design. | 5 OVERSIGHT City review, invoice approval, progress reports, FHWA milestone review. | 6 CLOSE-OUT Draft Action Plan, FHWA input, finance, final reporting, acceptance. |
| --- | --- | --- | --- | --- | --- |

| Consultant-led technical work - Document baseline safety analysis, crash data, and existing conditions. - Identify and prioritize high-risk locations and safety risk networks. - Engage the public and stakeholders through workshops, surveys, and public meetings. - Safety Action Plan components: risk mapping, proven countermeasures, equity considerations, cost estimates, phasing, and implementation strategies. - Priority corridors, including Main Street, advanced from concepts into safety-driven preliminary design appropriate for a Planning and Demonstration grant. | Proposed 12-month timeline Month 0: Grant agreement, NTP, FHWA kickoff. Months 1–2: Consultant procurement, contracting, systems setup. Months 3–5: Baseline safety analysis, crash review, and initial engagement. Months 6–8: Risk network analysis, countermeasure identification, continued engagement. Months 9–10: Draft Comprehensive Safety Action Plan and preliminary cost estimates. Months 11–12: FHWA review, revisions, Action Plan approval, close-out. |
| --- | --- |

| greenriver.utah.gov ¦ 460 E. Main St., Green River, UT 84525 | SS4A Planning and Demonstration Grant ¦ Updated: [June 2026] |
| --- | --- |